## Legend
The proposed pension Administration System must deliver a comprehensive, secure and scalable solution to support the Fund's operational and member service needs. The following provides a legend for how to respond to each requirement.
The following designated Priority ratings are defined as follows
Mandatory - These are mandatory requirements that must be implemented exactly as specified.
Not Required - These are items not required for this option.
The vendor must respond to each of the functional requirements by selecting one of the following Compliance descriptions.
We Agree - Existing system functionality will be configured to deliver the requirement.
Not Met - Existing functionality for this requirement does not exist and vendor can not and will not accommodate. Therefore this will not be included on your cost proposal.
Comment column is used by the vendor to explain potential exceptions to configurable or method to provide for the requirement through alternative means.
Please include information on compliance, implementation, approach and any additional capabilities your solution offers in the comment section.

## Requirements Summary
Category | Count
Application Support | 4
Application Support / Maintenance | 14
Change Management | 3
Conversion | 7
Data Protection / Recovery | 6
Documentation | 3
Enhancements | 5
Governance & Project Management | 21
Implementation | 9
Knowledge Transfer | 2
Onboarding and Project Kick-off | 5
Project Implementation | 10
Security | 6
Staffing & Team Responsibilities | 16
Testing | 30
Third‑Party & Integration Management | 10
Training | 16
Warranty | 14
Total | 181

## Service Requirements
Ref# | Category | Requirement Description | Option 1 – Custom Build | Option 1 – Compliance | Option 1 – Comment | Option 2 – COTS Required | Option 2 – Compliance | Option 2 – Comment
S.001 | Application Support | Bidder shall provide ongoing application support for production issues, defects, and operational questions. | Mandatory |  |  | Mandatory
S.002 | Application Support | Bidder shall describe in their response the support model, including resource locations and points of contact. | Mandatory |  |  | Mandatory
S.003 | Application Support | Bidder shall ensure continuity of system knowledge and minimize reliance on individual resources. | Mandatory |  |  | Mandatory
S.004 | Application Support | Bidder shall provide ongoing application support for incidents, defects, and service requests. | Mandatory |  |  | Mandatory
S.005 | Application Support / Maintenance | Bidder shall maintain and coordinate a schedule of planned maintenance activities with FABF. | Mandatory |  |  | Mandatory
S.006 | Application Support / Maintenance | Bidder shall provide advance notification of planned downtime in accordance with the SLA. | Mandatory |  |  | Mandatory
S.007 | Application Support / Maintenance | Bidder shall provide a formal Service Level Agreement (SLA) governing production support for the System for 10 years. | Not Required |  |  | Mandatory
S.008 | Application Support / Maintenance | System availability shall meet or exceed 99.5% monthly uptime, excluding FABF‑approved maintenance windows. | Mandatory |  |  | Mandatory
S.009 | Application Support / Maintenance | SLA shall define incident severity levels (Critical, High, Medium, Low) with public pension business impact definitions. | Mandatory |  |  | Mandatory
S.010 | Application Support / Maintenance | For Critical incidents, Bidder shall provide initial response within 1 hour and continuous work until resolution or approved workaround. | Mandatory |  |  | Mandatory
S.011 | Application Support / Maintenance | For High severity incidents, Bidder shall provide initial response within 4 business hours and target resolution within 2 business days. | Mandatory |  |  | Mandatory
S.012 | Application Support / Maintenance | SLA shall include a documented escalation path, including executive escalation roles. | Mandatory |  |  | Mandatory
S.013 | Application Support / Maintenance | Bidder shall provide monthly SLA performance reports to FABF. | Mandatory |  |  | Mandatory
S.014 | Application Support / Maintenance | Bidder shall meet defined response and resolution targets by incident severity. | Mandatory |  |  | Mandatory
S.015 | Application Support / Maintenance | Bidder shall provide operational support for the production environment, whether Bidder‑hosted or Bidder‑managed cloud (e.g., Azure or AWS), under FABF governance. | Mandatory |  |  | Mandatory
S.016 | Application Support / Maintenance | Bidder shall support operating systems, databases, middleware, and application platforms supporting the System. | Mandatory |  |  | Mandatory
S.017 | Application Support / Maintenance | Bidder shall maintain production, non‑production, and disaster recovery environments. | Mandatory |  |  | Mandatory
S.018 | Application Support / Maintenance | Legislative changes which apply to FABF administration occur frequently (at least annually). The bidder is required to commit resources to monitor proposed legislative changes with FABF to plan potential PAS changes. Development of changes should begin upon signature by the Governor for the State of Illinois with implementation of changes by the legislation effective date (typically 60 – 90 days after signature). Additionally, the Bidder shall provide comprehensive documentation related to the implementation, including a description of the purpose of the specific program and detailed user guidelines for proper use of the system. | Mandatory |  |  | Mandatory
S.019 | Change Management | Bidder shall follow formal change management procedures, including impact analysis and FABF approval prior to implementation. | Mandatory |  |  | Mandatory
S.020 | Change Management | All changes shall be tested in a non‑production environment prior to release. | Mandatory |  |  | Mandatory
S.021 | Change Management | Bidder shall provide release notes for all production deployments. | Mandatory |  |  | Mandatory
S.022 | Conversion | Bidder shall perform data conversion and migration from FABF legacy systems in accordance with a FABF‑approved Conversion Plan. This potentially could be into a Microsoft SQL Server database. | Mandatory |  |  | Mandatory
S.023 | Conversion | Bidder shall perform mock conversions, reconciliation, and validation prior to production cutover. | Mandatory |  |  | Mandatory
S.024 | Conversion | Bidder shall certify data conversion completeness, accuracy, and readiness for production use. | Mandatory |  |  | Mandatory
S.025 | Conversion | The vendor must develop and execute comprehensive data conversion and migration strategies that ensure data accuracy, completeness, and reconciliation between the legacy environment and the new system. | Mandatory |  |  | Mandatory
S.026 | Conversion | The vendor must configure and implement all system functionality and business rules necessary to satisfy the requirements of each functional roll‑out development period. | Mandatory |  |  | Mandatory
S.027 | Conversion | The vendor must define, document, and validate written procedures, methods, and checklists for data conversion, balancing, and reconciliation activities for each functional roll‑out. | Mandatory |  |  | Mandatory
S.028 | Conversion | The vendor must design, implement, and validate all required data bridges and interfaces to ensure seamless interoperability with internal and external systems. | Mandatory |  |  | Mandatory
S.029 | Data Protection / Recovery | Bidder shall support ongoing monitoring of data integrity and processing accuracy. | Mandatory |  |  | Mandatory
S.030 | Data Protection / Recovery | Bidder shall support recovery activities in the event of system or data failure. | Mandatory |  |  | Mandatory
S.031 | Data Protection / Recovery | Bidder shall ensure encryption, backup, retention, and logical segregation of FABF data, potentially using using immutable backup capabilities. | Mandatory |  |  | Mandatory
S.032 | Data Protection / Recovery | Bidder shall maintain and support a Disaster Recovery Plan covering applications, data, interfaces, and integrations. | Mandatory |  |  | Mandatory
S.033 | Data Protection / Recovery | Bidder shall support FABF‑defined Recovery Time Objectives (RTO) and Recovery Point Objectives (RPO) such as ≤ 4 hours and ≤ 15 minutes respectively. | Mandatory |  |  | Mandatory
S.034 | Data Protection / Recovery | Bidder shall participate in periodic disaster recovery testing and provide written certification of results. | Mandatory |  |  | Mandatory
S.035 | Documentation | Bidder shall maintain current system and operational documentation. | Mandatory |  |  | Mandatory
S.036 | Documentation | For Option 1, documentation shall be sufficient to support FABF independent system support and enhancement. | Mandatory |  |  | Not Required
S.037 | Documentation | Bidder shall maintain current operational, technical, and administrative documentation. | Mandatory |  |  | Mandatory
S.038 | Enhancements | Enhancement hours may be used for minor functional changes, configuration updates, reports, extracts, workflows, and regulatory changes not classified as defects. | Mandatory |  |  | Mandatory
S.039 | Enhancements | Enhancement requests shall be governed through a joint FABF/Bidder prioritization process. | Mandatory |  |  | Mandatory
S.040 | Enhancements | Bidder shall track and report enhancement hour usage to FABF on a regular basis. | Mandatory |  |  | Mandatory
S.041 | Enhancements | Bidder shall clearly state whether unused enhancement hours expire or may be carried forward. | Mandatory |  |  | Mandatory
S.042 | Enhancements | Bidder shall provide two hundred (200) hours per contract year for miscellaneous system enhancements. | Mandatory |  |  | Mandatory
S.043 | Governance & Project Management | Bidder shall provide transparency into incidents, enhancements, risks, and planned changes. | Mandatory |  |  | Mandatory
S.044 | Governance & Project Management | Bidder shall participate in periodic service governance and operational review meetings with FABF. | Mandatory |  |  | Mandatory
S.045 | Governance & Project Management | The vendor shall use a single, documented project management methodology to control and manage all aspects of solution development, implementation, and delivery. | Mandatory |  |  | Mandatory
S.046 | Governance & Project Management | The vendor shall produce quarterly executive‑level project reports suitable for senior leadership and governance bodies, incorporating key performance indicators, risk posture, and visual status summaries. | Mandatory |  |  | Mandatory
S.047 | Governance & Project Management | The vendor shall prepare and deliver weekly project status reports that summarize completed activities, upcoming work, schedule progress, risks, issues, and dependencies in alignment with the approved project plan. | Mandatory |  |  | Mandatory
S.048 | Governance & Project Management | The vendor shall establish, document, and maintain a formal decision management process to capture, track, and communicate all project decisions and pending decision items. | Mandatory |  |  | Mandatory
S.049 | Governance & Project Management | The vendor shall analyze all client‑submitted change requests and provide completed change request documentation, including impact analysis, within the contractually defined review period. | Mandatory |  |  | Mandatory
S.050 | Governance & Project Management | The vendor shall provide and maintain an online deliverable tracking repository that clearly identifies deliverable ownership, status, review cycles, and approval history. | Mandatory |  |  | Mandatory
S.051 | Governance & Project Management | The vendor shall document and communicate the cost, schedule, resource, and scope impacts of approved and proposed changes in sufficient detail to support informed decision‑making. | Mandatory |  |  | Mandatory
S.052 | Governance & Project Management | The vendor shall collaborate with the client’s project manager to develop, document, and maintain a comprehensive Project Management Plan covering scope, schedule, cost, resources, communications, and stakeholder management. | Mandatory |  |  | Mandatory
S.053 | Governance & Project Management | The vendor shall develop and incorporate a formal project governance structure into the Project Management Plan, including defined roles, escalation paths, and decision‑making authority. | Mandatory |  |  | Mandatory
S.054 | Governance & Project Management | The vendor shall document and manage a Requirements Management Plan that defines tools, roles, traceability methods, and processes for updating, approving, and communicating requirements changes. | Mandatory |  |  | Mandatory
S.055 | Governance & Project Management | The vendor shall conduct formal risk and issue reviews at least quarterly and report the status of mitigation activities, escalations, and residual risks to project stakeholders. | Mandatory |  |  | Mandatory
S.056 | Governance & Project Management | The vendor shall establish and operate a risk and issue management process that identifies, analyzes, prioritizes, mitigates, tracks, and reports project risks and issues throughout the project lifecycle. | Mandatory |  |  | Mandatory
S.057 | Governance & Project Management | The vendor shall develop and maintain a System Security Plan that addresses data protection, access controls, encryption, auditability, and compliance with applicable security requirements. | Mandatory |  |  | Mandatory
S.058 | Governance & Project Management | The vendor shall create, track, and manage Problem Incident Reports (PIRs), including classification, resolution, and reporting, for incidents occurring during data conversion, testing, and implementation activities. | Mandatory |  |  | Mandatory
S.059 | Governance & Project Management | The vendor shall periodically test and evaluate the effectiveness of project security controls, policies, and procedures, and document the results for client review. | Mandatory |  |  | Mandatory
S.060 | Governance & Project Management | The vendor must produce a Business Rules deliverable that clearly identifies all rules to be implemented in the system for each roll‑out phase and ensures traceability to approved requirements. | Mandatory |  |  | Mandatory
S.061 | Governance & Project Management | Bidder shall deliver and maintain FABF‑approved project phase deliverables, including plans, schedules, risk logs, and status reports. | Mandatory |  |  | Mandatory
S.062 | Governance & Project Management | Bidder shall manage project execution using a documented methodology appropriate for a public pension administration system. | Mandatory |  |  | Mandatory
S.063 | Governance & Project Management | Bidder shall support FABF review, approval, and acceptance of all phase deliverables prior to milestone completion. | Mandatory |  |  | Mandatory
S.064 | Implementation | Bidder shall provide one‑time implementation services to configure, deploy, and place the System into production in accordance with FABF‑approved plans. | Mandatory |  |  | Mandatory
S.065 | Implementation | Bidder shall deliver an Implementation Plan addressing cutover, stabilization, rollback, roles, responsibilities, and post‑go‑live support. | Mandatory |  |  | Mandatory
S.066 | Implementation | The vendor must ensure that all deliverables associated with each roll‑out are completed, reviewed, and approved in writing by the client prior to progression to subsequent phases. | Mandatory |  |  | Mandatory
S.067 | Implementation | The vendor must implement and validate security controls for each roll‑out in accordance with the approved Security Plan and applicable industry standards. | Mandatory |  |  | Mandatory
S.068 | Implementation | The vendor must ensure disaster recovery processes, environments, and procedures are operational, tested, and aligned with the roll‑out schedule. | Mandatory |  |  | Mandatory
S.069 | Implementation | The vendor must resolve all defects categorized as “critical” or “high” prior to delivery and ensure successful regression testing before any roll‑out is placed into production. | Mandatory |  |  | Mandatory
S.070 | Implementation | The vendor must document, track, and obtain approval for any remaining medium‑severity defects, including defined workarounds or remediation plans, prior to production deployment. | Mandatory |  |  | Mandatory
S.071 | Implementation | The vendor must certify that all roll‑out testing activities, including configuration, integration, and regression testing, have been successfully completed in accordance with the approved test plans. | Mandatory |  |  | Mandatory
S.072 | Implementation | The vendor must ensure that all user acceptance testing (UAT) deliverables and exit criteria are met and formally approved prior to production cutover. | Mandatory |  |  | Mandatory
S.073 | Knowledge Transfer | Bidder shall provide knowledge transfer sufficient to support long‑term FABF operational continuity. | Mandatory |  |  | Mandatory
S.074 | Knowledge Transfer | For Option 1 (Custom Build), Bidder shall support FABF’s ability to independently maintain and enhance the System. | Mandatory |  |  | Not Required
S.075 | Onboarding and Project Kick-off | The vendor shall work collaboratively with the client’s designated project manager to ensure that all project start‑up activities are completed, reviewed, and formally approved prior to the commencement of requirements confirmation or design activities. | Mandatory |  |  | Mandatory
S.076 | Onboarding and Project Kick-off | The vendor shall deliver a comprehensive System Implementation Methodology overview to client stakeholders at project initiation, clearly describing the implementation approach, phases, deliverables, roles, and governance structure. | Mandatory |  |  | Mandatory
S.077 | Onboarding and Project Kick-off | The vendor shall develop and deliver a formal Project Kick‑off presentation that establishes project objectives, scope, schedule, roles and responsibilities, communication protocols, and success criteria. | Mandatory |  |  | Mandatory
S.078 | Onboarding and Project Kick-off | The vendor shall confirm project readiness by validating that required resources, tools, environments, and documentation are in place prior to the start of execution activities. | Mandatory |  |  | Mandatory
S.079 | Onboarding and Project Kick-off | The vendor shall document and obtain client approval of all onboarding and kick‑off deliverables as part of the baseline Project Management Plan. | Mandatory |  |  | Mandatory
S.080 | Project Implementation | The vendor shall collaborate with the client’s designated project manager to plan, execute, and obtain formal approval of all data conversion, system configuration, security setup, and production deployment activities. | Mandatory |  |  | Mandatory
S.081 | Project Implementation | The vendor shall be responsible for the end‑to‑end support of all systems, environments, infrastructure components, and tools required to deliver the solution throughout the duration of the implementation. | Mandatory |  |  | Mandatory
S.082 | Project Implementation | The vendor shall provide dedicated, full‑time transition support during critical pre‑ and post‑cutover periods, including participation by key project leadership through a defined number of successful production cycles. | Mandatory |  |  | Mandatory
S.083 | Project Implementation | The vendor shall design, document, and implement a comprehensive security approach that addresses access controls, authentication, data protection, auditability, vulnerability management, and secure remote access in accordance with industry best practices. | Mandatory |  |  | Mandatory
S.084 | Project Implementation | The vendor shall perform all necessary configuration, customization, programming, and business rule implementation required to meet the functional and technical requirements of each implementation phase. | Mandatory |  |  | Mandatory
S.085 | Project Implementation | The vendor shall develop and maintain detailed functional, technical, and architectural design documentation at a level sufficient to support solution configuration, integration, and long‑term maintainability. | Mandatory |  |  | Mandatory
S.086 | Project Implementation | The vendor shall deliver a fully integrated solution that includes approved system functionality, security controls, online access, reporting, data management, disaster recovery capabilities, and validated interfaces with internal and external systems. | Mandatory |  |  | Mandatory
S.087 | Project Implementation | The vendor shall define, document, and implement all business rules within the solution and ensure traceability between business requirements, system configuration, and delivered functionality. | Mandatory |  |  | Mandatory
S.088 | Project Implementation | The vendor shall design, build, and support all required system interfaces and data exchanges necessary to ensure seamless interoperability between the solution and all dependent applications. | Mandatory |  |  | Mandatory
S.089 | Project Implementation | The vendor shall support the client in addressing internal or external security audit findings related to the implemented solution and provide remediation assistance as required to achieve compliance. | Mandatory |  |  | Mandatory
S.090 | Security | The vendor must support the client in responding to internal or external security audit findings related to roll‑out activities and implement corrective actions as required. | Mandatory |  |  | Mandatory
S.091 | Security | Bidder shall support security patching and vulnerability remediation. | Mandatory |  |  | Mandatory
S.092 | Security | Bidder shall promptly notify FABF of any security incident affecting the System. | Mandatory |  |  | Mandatory
S.093 | Security | Bidder shall support audits or reviews requested by FABF or its auditors. | Mandatory |  |  | Mandatory
S.094 | Security | Bidder shall provide ongoing security administration and monitoring for the hosted environment. | Mandatory |  |  | Mandatory
S.095 | Security | Bidder shall remediate identified security vulnerabilities within agreed‑upon timelines. | Mandatory |  |  | Mandatory
S.096 | Staffing & Team Responsibilities | The team shall implement strong program management practices, including change request management, issue management, risk management, and decision tracking, in accordance with the approved project governance framework. | Mandatory |  |  | Mandatory
S.097 | Staffing & Team Responsibilities | The vendor shall maintain ongoing communication with all vendor project team members and FABF stakeholders to ensure alignment with project requirements and FABF expectations. | Mandatory |  |  | Mandatory
S.098 | Staffing & Team Responsibilities | The team shall be responsible for mapping, transforming, and loading data from the legacy system to the new system in accordance with approved conversion requirements. | Mandatory |  |  | Mandatory
S.099 | Staffing & Team Responsibilities | The team shall be responsible for executing all activities defined in the approved Data Conversion Plan. | Mandatory |  |  | Mandatory
S.100 | Staffing & Team Responsibilities | The team shall be dedicated primarily to the FABF project with minimal competing assignments from the vendor. | Mandatory |  |  | Mandatory
S.101 | Staffing & Team Responsibilities | The team shall provide business and functional expertise, guidance, and recommendations in support of solution design, configuration, and implementation. | Mandatory |  |  | Mandatory
S.102 | Staffing & Team Responsibilities | The team shall provide onsite presence at FABF during key project activities, including testing, cutover, and other critical milestones, as required. | Mandatory |  |  | Mandatory
S.103 | Staffing & Team Responsibilities | The team shall be authorized by the vendor to make binding commitments to FABF related to project execution and the vendor’s scope of work. | Mandatory |  |  | Mandatory
S.104 | Staffing & Team Responsibilities | The vendor shall replace any approved departing personnel with individuals who meet or exceed the qualifications and experience of the personnel being replaced. | Mandatory |  |  | Mandatory
S.105 | Staffing & Team Responsibilities | The vendor shall maintain staffing continuity and shall not replace key project personnel without prior written approval from FABF, except as contractually permitted. | Mandatory |  |  | Mandatory
S.106 | Staffing & Team Responsibilities | The vendor shall allow FABF the right to approve or reject proposed replacement personnel prior to assignment and at any time during the project. | Mandatory |  |  | Mandatory
S.107 | Staffing & Team Responsibilities | The vendor shall respond promptly to FABF requests to replace key personnel or additional roles due to performance concerns. | Mandatory |  |  | Mandatory
S.108 | Staffing & Team Responsibilities | The vendor shall ensure that assigned personnel have a minimum of three (3) years of experience leading large‑scale system conversion activities within the timeframe specified in the RFP. | Mandatory |  |  | Mandatory
S.109 | Staffing & Team Responsibilities | The team shall support FABF testing activities, including development of test plans, coordination of conversion testing, tracking of testing progress, and reporting of testing metrics. | Mandatory |  |  | Mandatory
S.110 | Staffing & Team Responsibilities | The team shall review, acknowledge, and comply with FABF’s code of ethics on an annual basis throughout the duration of the project. | Mandatory |  |  | Mandatory
S.111 | Staffing & Team Responsibilities | The vendor will not reassign any Key Project Personnel (Project Manager, Functional Lead and Conversion Lead) for at least a year after that Key Project Personnel member begins work at FABF unless the vendor has received prior written approval from FABF for the staffing change. The vendor acknowledges that, except for termination, a $25,000 penalty may apply should Key Project Personnel be removed from the project without the written consent of the FABF Project Manager. | Mandatory |  |  | Mandatory
S.112 | Testing | Bidder shall plan, execute, and support system, integration, regression, performance, and security testing prior to production release. | Mandatory |  |  | Mandatory
S.113 | Testing | Bidder shall support User Acceptance Testing (UAT), including defect resolution and retesting. | Mandatory |  |  | Mandatory
S.114 | Testing | Bidder shall ensure no Critical or High severity defects remain unresolved prior to production deployment. | Mandatory |  |  | Mandatory
S.115 | Testing | Bidder shall provide test results, certifications, and evidence of successful testing prior to go‑live. | Mandatory |  |  | Mandatory
S.116 | Testing | Bidder shall support performance and volume testing sufficient to meet SLA and operational requirements. | Mandatory |  |  | Mandatory
S.117 | Testing | The vendor shall certify in writing—signed by the vendor Project Manager and vendor Test Lead - that all defined pre‑cutover test criteria have been met for each functional release prior to production cutover. | Mandatory |  |  | Mandatory
S.118 | Testing | The vendor shall ensure vendor acceptance testing is executed and formally signed off in accordance with the approved Master and Detailed Test Plans prior to production cutover. | Mandatory |  |  | Mandatory
S.119 | Testing | The vendor shall ensure user acceptance testing (UAT) is executed and formally signed off by the client in accordance with the approved test plans prior to production cutover. | Mandatory |  |  | Mandatory
S.120 | Testing | The vendor shall verify and document completion and sign‑off of all required security testing and disaster recovery testing activities prior to production cutover. | Mandatory |  |  | Mandatory
S.121 | Testing | The vendor shall ensure benefit payroll reconciliation to the preceding pay period is completed (where applicable) and documented as part of the release cutover readiness evidence. | Mandatory |  |  | Mandatory
S.122 | Testing | The vendor shall ensure no defects categorized as “critical” or “high” remain unresolved prior to cutover, and that any “medium” defects have documented workarounds and agreed remediation actions. | Mandatory |  |  | Mandatory
S.123 | Testing | The vendor shall ensure UAT and conversion testing activities reach 100% completion and that all related deliverables are accepted and approved by the client prior to cutover. | Mandatory |  |  | Mandatory
S.124 | Testing | The vendor shall validate and certify that the solution operates with no “critical” or “high” defects at the time of production release. | Mandatory |  |  | Mandatory
S.125 | Testing | The vendor shall ensure 100% of in‑scope data is converted into the production system in accordance with the approved Data Conversion Plan and provide evidence of completion. | Mandatory |  |  | Mandatory
S.126 | Testing | The vendor shall demonstrate that 100% of to‑be‑converted data is successfully converted and fully reconciled using client‑approved reconciliation methods and reporting. | Mandatory |  |  | Mandatory
S.127 | Testing | The vendor shall execute all UAT tests per the approved Test Plan, including parallel tests where applicable, and maintain auditable records of results. | Mandatory |  |  | Mandatory
S.128 | Testing | The vendor shall resolve all “critical” and “high” defects identified during UAT and provide regression test evidence demonstrating successful resolution. | Mandatory |  |  | Mandatory
S.129 | Testing | The vendor shall perform stress, volume, and performance testing in accordance with the Detailed Test Plan and document that performance criteria and service levels are met. | Mandatory |  |  | Mandatory
S.130 | Testing | The vendor shall develop and execute integration tests to verify that information is exchanged correctly between all solution components and interfacing systems. | Mandatory |  |  | Mandatory
S.131 | Testing | The vendor shall develop and maintain a regression test suite that confirms previously repaired defects do not recur in subsequent releases. | Mandatory |  |  | Mandatory
S.132 | Testing | The vendor shall obtain written client approval to proceed with Vendor Acceptance Testing based on the approved requirements and defined entry criteria. | Mandatory |  |  | Mandatory
S.133 | Testing | The vendor shall perform recovery testing to validate backup and restore capability and provide documented evidence of successful execution. | Mandatory |  |  | Mandatory
S.134 | Testing | The vendor shall perform disaster recovery scenario testing that demonstrates recoverability from isolated incidents (e.g., hardware/application failure) and from a major incident requiring use of the client’s disaster recovery site. | Mandatory |  |  | Mandatory
S.135 | Testing | The vendor shall perform security testing (which may include vulnerability scanning or penttest) to validate confidentiality, integrity, authentication, availability, authorization, and non‑repudiation controls, and provide results acceptable to the client. | Mandatory |  |  | Mandatory
S.136 | Testing | The vendor shall perform system testing that validates design and verifies expected functionality across components for each functional release. | Mandatory |  |  | Mandatory
S.137 | Testing | The vendor shall perform unit testing designed to identify defects early in the development lifecycle and document results prior to handoff for independent testing and UAT. | Mandatory |  |  | Mandatory
S.138 | Testing | The vendor shall certify data conversion readiness for training, testing, and implementation according to criteria established in the approved Data Conversion Plan. | Mandatory |  |  | Mandatory
S.139 | Testing | The vendor shall provide the client with a complete copy of the Problem Incident Report (PIR) system and the full database of reported incidents at project conclusion, including those reported by vendor and client testing resources. | Mandatory |  |  | Mandatory
S.140 | Testing | The vendor shall design and document test cases/scenarios/user stories that ensure all requirements in the Requirements Traceability Matrix (RTM) are tested, and include them in the Test Scripts deliverable. | Mandatory |  |  | Mandatory
S.141 | Testing | The vendor shall define and document a release management model and associated regression testing expectations for each functional release, including how changes are promoted, validated, and authorized for production. | Mandatory |  |  | Mandatory
S.142 | Third‑Party & Integration Management | The vendor shall design, configure, and implement all required system interfaces and integrations necessary to support interoperability between the solution and internal and external systems. | Mandatory |  |  | Mandatory
S.143 | Third‑Party & Integration Management | The team shall coordinate and collaborate with the legacy system vendor to support a smooth transition of data, configurations, and system knowledge. | Mandatory |  |  | Mandatory
S.144 | Third‑Party & Integration Management | The team shall perform comprehensive integration testing to verify that data and transactions are exchanged accurately and reliably between all interfacing systems. | Mandatory |  |  | Mandatory
S.145 | Third‑Party & Integration Management | The team shall manage and oversee all relationships with subcontracted or hosted third‑party service providers associated with the solution. | Mandatory |  |  | Mandatory
S.146 | Third‑Party & Integration Management | The vendor shall participate in vulnerability assessments or security reviews conducted by FABF or FABF‑selected third parties and provide required technical information and remediation support. | Mandatory |  |  | Mandatory
S.147 | Third‑Party & Integration Management | The vendor shall ensure continuity of hosting or integration services in the event a third‑party provider ceases operations, including transition to an alternate provider or vendor‑managed services. | Mandatory |  |  | Mandatory
S.148 | Third‑Party & Integration Management | The team shall ensure that all third‑party integrations comply with FABF security, data protection, and interface standards. | Mandatory |  |  | Mandatory
S.149 | Third‑Party & Integration Management | The team shall document all interfaces, integration points, data exchanges, and dependencies to support long‑term maintenance and operational support. | Mandatory |  |  | Mandatory
S.150 | Third‑Party & Integration Management | The team shall provide FABF and any FABF‑designated oversight project manager with access to all project materials, documentation, and communications related to third‑party integrations. | Mandatory |  |  | Mandatory
S.151 | Third‑Party & Integration Management | The vendor shall remain accountable for the performance, reliability, and security of all third‑party integrations delivered as part of the solution. | Mandatory |  |  | Mandatory
S.152 | Training | The vendor must complete all required user documentation, training materials, and end‑user support artifacts before the conclusion of each functional roll‑out. | Mandatory |  |  | Mandatory
S.153 | Training | The team shall develop and deliver training materials that enable FABF staff to effectively use the solution and associated business processes. | Mandatory |  |  | Mandatory
S.154 | Training | The team shall deliver training in multiple formats, including classroom instruction, workshops or laboratories, and online training with hands‑on exercises, as appropriate. | Mandatory |  |  | Mandatory
S.155 | Training | The team shall provide multiple training programs ranging from general user familiarization to role‑based system operation, configuration, and reporting. | Mandatory |  |  | Mandatory
S.156 | Training | The team shall customize all training content specifically for the FABF solution and FABF business processes, including normal processing and correction scenarios. | Mandatory |  |  | Mandatory
S.157 | Training | The team shall incorporate participant feedback and evaluation results to continuously improve training effectiveness. | Mandatory |  |  | Mandatory
S.158 | Training | The team shall document and implement an evaluation process to assess participant understanding and readiness at the conclusion of each training session. | Mandatory |  |  | Mandatory
S.159 | Training | The team shall work collaboratively with FABF staff to design and store training materials in a manner that supports long‑term maintenance by FABF. | Mandatory |  |  | Mandatory
S.160 | Training | The team shall provide training on user responsibilities and required actions to support seamless integration with interfacing systems such as imaging, workflow, and related applications. | Mandatory |  |  | Mandatory
S.161 | Training | The team shall develop and deliver end‑to‑end work process documentation that supports each functional roll‑out development period. | Mandatory |  |  | Mandatory
S.162 | Training | The team shall deliver hands‑on training through workshops and laboratory environments that allow users to practice real‑world scenarios. | Mandatory |  |  | Mandatory
S.163 | Training | The team shall finalize the Draft Training Plan during project start‑up in collaboration with FABF and obtain formal approval prior to training execution. | Mandatory |  |  | Mandatory
S.164 | Training | The team shall document the training and knowledge‑transfer approach to ensure FABF technical and business staff can administer and support the system after project completion. | Mandatory |  |  | Mandatory
S.165 | Training | The team shall ensure training materials address system functionality, navigation, data entry, reporting, and use of integrated Microsoft Office and scheduling tools. | Mandatory |  |  | Mandatory
S.166 | Training | The team shall ensure all training deliverables are completed, reviewed, and approved by FABF prior to the conclusion of the training phase. | Mandatory |  |  | Mandatory
S.167 | Training | The team shall schedule and deliver training sessions in coordination with the overall project timeline to support testing, cutover, and post‑go‑live readiness. | Mandatory |  |  | Mandatory
S.168 | Warranty | The vendor shall warrant that the implemented solution will operate, in its entirety, in accordance with all contractual, functional, and technical requirements during the warranty period. | Mandatory |  |  | Mandatory
S.169 | Warranty | The vendor shall resolve all defects identified during the warranty period at no additional cost to the client. | Mandatory |  |  | Mandatory
S.170 | Warranty | The vendor shall provide post‑go‑live stabilization support to ensure system reliability, performance, and issue resolution following production deployment. | Mandatory |  |  | Mandatory
S.171 | Warranty | The vendor shall include within the warranty any incidents or defects identified prior to production that were not fully resolved at the time a functional release was placed into production. | Mandatory |  |  | Mandatory
S.172 | Warranty | The vendor shall perform all warranty services in accordance with the requirements defined in the RFP and the executed agreement. | Mandatory |  |  | Mandatory
S.173 | Warranty | The vendor shall upgrade system software components made generally available during the term of the agreement at no additional cost to the client. | Mandatory |  |  | Mandatory
S.174 | Warranty | The vendor shall ensure that warranty support covers all system components, integrations, and configurations delivered as part of the implementation. | Mandatory |  |  | Mandatory
S.175 | Warranty | The vendor shall document, track, and report warranty issues, including root cause, corrective actions, and resolution status, in a manner acceptable to the client. | Mandatory |  |  | Mandatory
S.176 | Warranty | The vendor shall support the client in defining and measuring post‑implementation success criteria, including operational stability and performance benchmarks following go‑live. | Mandatory |  |  | Mandatory
S.177 | Warranty | The vendor shall transition warranty support activities in an orderly manner to the client or a designated support provider at the conclusion of the warranty period, including knowledge transfer and documentation handoff. | Mandatory |  |  | Mandatory
S.178 | Warranty | Bidder shall provide a minimum twelve (12) month warranty following production go‑live. | Mandatory |  |  | Mandatory
S.179 | Warranty | Bidder shall resolve all defects identified during the Warranty Period at no additional cost to FABF. | Mandatory |  |  | Mandatory
S.180 | Warranty | Bidder shall resolve any pre‑existing defects not resolved prior to go‑live as part of warranty obligations. | Mandatory |  |  | Mandatory
S.181 | Warranty | Warranty services shall be separate from and shall not reduce ongoing service or SLA obligations. | Mandatory |  |  | Mandatory